## Operational Plan 2025 2026
Strategic Direction (Select from dropdown options) | Key Commitment (Select from dropdown options) | Activity / Tactic | Accountable (One name only) | Responsible (Supporting the "doing") | Outcome (Measurement of success) | Target (Completion Date) | Priority Level (Low, Medium or High) | Progress | Required Resources (Time, materials, training, etc.) | Notes (Next steps, etc.)
1. Reenergized Capacity, Rejuvenated Culture | 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people | Draft a policy promoting organizational opportunities for professional growth | Sherry | Dorothy & Sharon | Policy created and approved | February 16 2024 | High | Completed |  | Policy has been created. Review at October Directors meeting. This policy is completed H:\Policy in Progress\2025.
| 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people | Explore options for better work/life balance | Leiann | Dorothy & Jordan | Have researched, created & implemented minimum of 2 new strategies, i.e. Mental health strategies, flexible work options etc. | March 31 2025 | Medium | Between 75% and 99% |  | Staff Satisfaction survey created, dispursed, compiled & completed by January 2025.Staff communication on steps to staff March 31, 2025. Outcome of surveys resulted in an increase in salary scale and pension benefits, approved by Board and will be implemented upon completion of Pay equity project in 2026 2027. Early office closures on day before long weekends implemented
| 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people | Review of renumeration package for employees - utilize recent salary surveys published by OCSA & partners & HPCO & investigate pension options. | Sherry | Leiann & Dorothy | Recommendation to board for 24/25 budget year | March 31 2025 | Medium | Between 75% and 99% | Business Case for HOOPP | Received compensation reports from HPCO and OCSA+ partners. Sherry and Dorothy attended HOOP presentation, costing completed in-house. Attended second presentation on a different plan for comparision. Update - contract with White & Gale to review compensation package. Project target completetion June 30 2026. Business case for HOOPP pension target Q1 2026 2027
| 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people | Create a volunteer strategy #engaging volunteers #understanding what we do well #Advisory Committee #Surveys | Leiann | Colleen, Nancy, Jenny | Vol committee in place. Create & completed Volunteer survey, interviews. Needs & wants identified. Strategies created. | March 31 2025 | Medium | Completed |  | Volunteer survey completed - 106 respondents. Results being compiled for dissemination. Committee framework is in progress. Vol committee formed, as of July 16th, 2024. Meet bi-monthly reviewing policies, volunteer retention strategies and Volunteer appreciation advice. Volunteer Survey 2026 sent out Feb. 2026
| 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people | Investigate EAP supports for all employees. |  | Dorothy | Recommendation to board for 24/25 budget year. | Feb 28 2024 | Medium | Completed | $2.77/person/month. | Included in budget in April 2024. All employees now have EAP program available. The premium for 2025-26 is now $1.75/person/month
1. Reenergized Capacity, Rejuvenated Culture | 1.2 Prioritizing healthy succession across all core roles | Create a succession plan document for key positions in the organization including Board, Senior Management and other identified key positions. | Jordan | Dorothy | Plan completed and approved by Board | March 31 2024 | High | Between 1-25% | 9 box exercise training-1 hour | Policy approved at Board meeting in March 2024. Succesion Planning for key roles through a 9 box exercise to be completed in Q2 of 2026-27
| 1.2 Prioritizing healthy succession across all core roles | Knowledge Transfer Template | Jordan | Dorothy | Template completed and in use. | June 30 2024 | High | Completed |  | Sample provided to new CEO complete
| 1.2 Prioritizing healthy succession across all core roles | Job Description Review | Jordan | Dorothy | Review Completed | Sept 30 2024 | High | Between 75% and 99% |  | 95% of job descriptions have been reviewed and updated.
1. Reenergized Capacity, Rejuvenated Culture | 1.3 Driving fundraising strategies to promote financial stability | Clarify & confirm role of the CCN Fundraising Committee | Joel | Jordan | consensus on Terms of Reference | March 31 2027 | Medium | Between 1-25% |  | ToR discussed at Feb meeting with revisions made to come back in April. Waiting for direction from Joint Governance Committee
| 1.3 Driving fundraising strategies to promote financial stability | Review relationship between CCN Fundraising and Ed's House Foundation fundraising | Joel | Jordan |  | March 31 2027 | Medium | Between 25 and 75% |  | With CCN fundraising shortfall, a full strategy needs to be developed including opportunities, personnel and execution. Until Now we've always done what's been done in the past. Relationship agreement presented and reviewed by joint governance board committee
| 1.3 Driving fundraising strategies to promote financial stability | Review involvement of CCN staff & volunteers within fundraising strategy | Joel | Jordan & Dorothy |  | March 31 2027 | Low | Paused or Delayed |  | Not a priority
| 1.3 Driving fundraising strategies to promote financial stability | Consistent fundraising messaging across all platforms (social media & website) | Joel | Samantha |  | March 31 2027 | Medium | Between 25 and 75% |  | Standard branding look for all materials complete. Need to formalize dates and plans. Waiting on direction from joint board governance committee. Draft communcation plan created ready to deploy
| 1.3 Driving fundraising strategies to promote financial stability | Re-design/re-launch of our website | Joel | Samantha & Tina |  | March 31 2027 | Low | Paused or Delayed | $20,000 for website creation | April 24 - review feedback received from current users of website. RFP Draft complete. Waiting on direction from joint board governance committee
| 1.3 Driving fundraising strategies to promote financial stability | Develop a fundraising plan - build/update - communicate with internal staff & volunteer where appropriate | Joel | Samantha |  | March 31 2027 | Medium | Paused or Delayed |  | Premliminary meeting held. Draft Emergency plan written. Needs review and input.
2. Cohesive Identity, Empowered Community | 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community | Using an external facilitator, evaluate communication & branding | Joel | Samantha & Colleen | clearly define the brand of CCN in the minds of our audience. | June 1 2025 | Low | Paused or Delayed |  | Consideration of external consultant on audience recognition on what CCN does "Service,Support,Connection" when promoting programs.
| 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community | Education of various departments to volunteer base | Leiann | Colleen, Nancy, Kelly, Jordan, Sherry | Ensuring all volunteers are aware of programs and services within CCN. |  | Low | Completed |  | In-person County wide volunteer drop-in events twice a year. Program specific volunteer education and meetings completed and on-going. Education incl all CCN programs at volunteer orienation
2. Cohesive Identity, Empowered Community | 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community | Improved orientation of new staff during onboarding process ensuring full organization review of programs & Services | Jordan | Dorothy, Colleen, Nancy, Leiann, Sherry | In-person twice a year to provide in-depth information. High light opportunities available to staff. | 2024-08-01 | High | Completed |  | Created payroll deduction form. New staff orientations planned 3 times per year in Mar/July/Nov with a new and revised presentation deck
| 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community | Investigate necessity of team building across agency (in particular between client services and hospice) | Jordan | Dorothy, Leiann, Sherry | One annual staff day, staff days (movie night, candy bar, skate night) | Sept 30 2024 | Medium | Completed |  | Annual staff day held in 2025/26 and moving forward
| 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community | Create Brand Ambassadors from our staff and volunteers | Joel | Jordan, Sherry & Leiann, Dorothy | Education and tools on what we do, how we do it, success etc. Potential speakers in community. | Dec 31 2025 | Low | Paused or Delayed | create a pool of people and resources to use in the ocmmunity | Create/Update presentation package and coordinate with Volunteer Coordinators
2. Cohesive Identity, Empowered Community | 2.2 Increasing community awareness through ongoing outreach and reciprocal relationships | Continue to focus on expertise in volunteering within Northumberland County | Leiann | Colleen, Nancy | Researched and Hosted min. 2 Volunteer Leader education sessions for County Vol. Leaders | March 31 2025 | Low | Completed |  | Volunteer Recruitment Coordinator now chairing a committee of County Volunteer Leaders which also includes skills and resource sharing and education. Complete and is ongoing.
| 2.2 Increasing community awareness through ongoing outreach and reciprocal relationships | Ensure involvement in OHTN in relevant areas | Jordan | Sherry, Leiann |  | 2024-01-01 | High | Completed |  | CEO continues on OHTN Collaboration Council. Staff will be assigned to support working groups once formed. Leiann on OHT-N sub-committee's OAWG and ROC and CSS Collaborative with reps of various OHT's.
| 2.2 Increasing community awareness through ongoing outreach and reciprocal relationships | Membership in Chambers of Commerces across the County - Board Participation | Joel |  | Make connections with business community for fundraising and awareness. | Dec 31 2024 | Low | Paused or Delayed |  | Memberships currently active in Trent Hills and Central N'land Chambers
| 2.2 Increasing community awareness through ongoing outreach and reciprocal relationships | Actively identify staff participation on relevant Board, Committees and Networks and encourage participation. | Jordan | Joel, Leiann, Sherry | Staff & committee's identified, promotion to staff & staff placement completed. | March 31 2025 | Low | Completed |  | Jordan to invite program staff to board meetings in Q4 2026 2027 and future fiscal years
| 2.2 Increasing community awareness through ongoing outreach and reciprocal relationships | Investigate CareDove link to website | Andrew | Samantha, Leiann | decision on use of caredove | Sept 30 2025 | Medium | Completed |  | As of January of 2025 the link to Caredove within the OHT-N site is complete.Waiting on new website.
2. Cohesive Identity, Empowered Community | 2.3 Empowering our team and supporters with the information and tools to be champions | Providing easy to understand financials to staff for awareness | Jordan | Joel |  | Dec 30 2024 | Medium | Completed |  | Infographics, financial stories to start October 2024. Jordyn presents financials to leadership team and managers monthly as an educaitonal tool
| 2.3 Empowering our team and supporters with the information and tools to be champions | Client and volunteer stories - share for impact regularly | Joel | Samantha |  | Ongoing | Medium | Between 1-25% |  | Have started some client interviews. First test used for CCN mailer in December 2025 and ongoing
| 2.3 Empowering our team and supporters with the information and tools to be champions | Ensure process for sharing client surveys and testimonials both internally and in our marketing | Joel | Leiann, Sherry, Samantha |  | March 30 2025 | Low | Between 25 and 75% |  | Waiver signed for all client, volunteer interactions complete. Donor Relations to gather and sort additional testamonials. Feedback policy under review and repository made a priority for 2026-27
| 2.3 Empowering our team and supporters with the information and tools to be champions | Create videos - draft content strategy | Joel | Samantha | first start of videos (MOW & Grief Group individual) - find organic stories | Sept 1 2024 | Low | Between 25 and 75% |  | Camera purchases. Determine content and schedule of interviews. First interview complete in Dec 2024-(Lorne)
3. Accessible Programs, Quality Services | 3.1 Focusing on the effective implementation of recent enhancements to service delivery | revisit our purpose for programs through evaluation and Quality Improvement approach | Jordan | Leiann, Sherry | QI process in place. QI committee created to evaluate 1-2 programs per quarter. | March 31 2025 | Medium | Between 25 and 75% |  | Feb 2024 - Create a Q1 committee of Managers to determine a process/template on how best to evaluate program areas. Client surveys distributed and received during Q4 2023-24 (350 responses received). Each department is currently evaluating one program each and this process will be on-going. Benchmarking presented on programs in February 2026. QI committee to be revamped in 2026-27
| 3.1 Focusing on the effective implementation of recent enhancements to service delivery | Initiate an Accessiblity Committee to review and ensure compliance with agency comitments with the Accessiblity for Ontarioans with Disabilities Act | Jordan |  | Committee created with a Terms of Reference and Work Plan. Accessiblity Plan posted on website, circulated to staff and volunteers and available to the public. | 2024-09-01 | High | Between 75% and 99% | Research various plans to adapt. | Worked with Cramahe and Trent Hills auditing team to ensure compliance with AODA in Transporation. Started Health Equity Committee in Q3 25/26. Due to many staffing changes Transp Accessibility Comm planning ongoing.
| 3.1 Focusing on the effective implementation of recent enhancements to service delivery | Ongoing commitment to HPCO Accreditation | Sherry | Sharon, Jordan | HPCO Accreditation maintained, interim report due Feb 2024, New application in 2025. | 2025-12-01 | High | Completed | Continuing to work on requirements for 2025 renewal. | Interim report submitted to HPCO February. Entered into next cycle accreditation submission. Accreditation appoved to August 2028.
| 3.1 Focusing on the effective implementation of recent enhancements to service delivery | Research agency wide accreditation options | Jordan | Sherry, Leiann | Direction determined regarding agency accreditation. | March 31st 2025 | Medium | Paused or Delayed | Director's discussed benefits or lack of, to have agency accreditation considering workload of doing so. | Direction to be provided after strateic planning development
| 3.1 Focusing on the effective implementation of recent enhancements to service delivery | Access formal and qualified ethics support tailored to the needs of CCN to ensure an ethcial approach within all aspects of service delivery and care. | Sherry | Jordan, Leiann, Sherry | Demonstrate a strong relationship with the Ontario Shores to support an agency Ethical Framework including staff and volunteer training and support, administrative review of policies and processes, access to ethical support as required. | Ongoing | Medium | Completed | Contract re-signed, ongoing review of annual workplan. | Ongoing staff and volunteer education sessions held and planned, access to external ethics education. Staff introductions made with information on access to services. / Client Services Ethics education held in Nov. 2024 to encourage participation within this division of CCN. MOU signed for current year. MOU with CEREN not renewed for 2026. MOU being undertaken with Ontario Shores.
3. Accessible Programs, Quality Services | 3.2 Collaborating across our community to streamline access to service | Investigating how to maximize current IT connectivity through platforms like Caredove, Epic, Oceans, Shiip and Connecting Ontario | Andrew | Jordan, Sherry, Leiann | Shiip presentation given but now not appropriate. | March 31 2026 | Medium | Completed |  | Begin April 2024 Shiip - not a viable option. Awaiting Connecting Ontario. Need awareness of OHTN Digital Health Committee Plan.
| 3.2 Collaborating across our community to streamline access to service | Phone connectivity between Client Services and Hospice Services | Andrew | Leiann, Sherry | Investigate the need for phone transfers between client services and hospice services. | March 31 2026 | Medium | Completed |  | assessed # of calls being transferred between CS to HS - looking for a simple system to improve client transfers. Have decided that this connection is unnecessary.
3. Accessible Programs, Quality Services | 3.3 Modelling effective, engaging volunteer management practices | Proactively explore additional volunteer practices ie Volunteer Northumberland | Leiann | Colleen, Kelly, Nancy | Researched & engaged opportunities with Volunteer Northumberland and similar groups. | Dec 31 2024 | Low | Completed |  | Met with operators of Volunteer Northumberland and no further opportunities for use of site discovered. Joined Trent Hills Chamber ongoing Virtual Volunteer fair. Will continue to investigate opportunities.
| 3.3 Modelling effective, engaging volunteer management practices | Mentorship for other volunteer organization | Leiann | Colleen, Kelly, Nancy |  | March 31 2026 | Medium | Completed |  | Survey sent to various County Volunteer professionals to identify wants and needs for education, knowledge sharing meetings, unexplored opportunities etc. Surveys complete-Group will meet quarterly with 8 County organizations participating / ongoing in 2025-2026
| 3.3 Modelling effective, engaging volunteer management practices | Provide leadership and active participation in volunteer inititiaives around the county | Leiann | Colleen, Kelly, Nancy |  | march 31 2026 | Medium | Completed |  | Participating in a virtual volunteer fair ongoing through the Trent Hills Community Directory. Took the lead creating In-person Vol fair in Cobourg on Sept. 25, 2024 /and will do so annually. Participate in multiple Wellness Fairs and Ageing Well fairs throughout the County.

## Directions and Commitments
Strategic Directions | Impact Statements | Strategic Commitments
1. Reenergized Capacity, Rejuvinated Culture | By 2027, we will have implemented strategies to strengthen our staff and volunteer capacity, refresh our workplace culture, and enable financial flexibility for intentionally investing in and maintaining a healthy organization. | 1.1 Reinforcing our staff and volunteer capacity through renewed strategies for attracting and retaining great people
1.2 Prioritizing healthy succession across all core roles
1.3 Driving fundraising strategies to promote financial stability
2. Cohesive Identity, Empowered community | By 2027, we will have enhanced our brand across Northumberland, built a strong network of champions, and increased awareness of the breadth of services and programs we offer to all age groups. | 2.1 Building a cohesive brand that supports our healthy reputation and increases our visibility across our community
2.2 Increasing community awareness through ongoing outreach and reciprocal relationships
2.3 Empowering our team and supporters with the information and tools to be champions
3. Accessible Programs, Quality Services | By 2027, we will have effectively implemented meaningful changes to our programs and services through consistency, continuous improvement, and being an active community partner. | 3.1 Focusing on the effective implementation of recent enhancements to service delivery
3.2 Collaborating across our community to streamline access to service
3.3 Modelling effective, engaging volunteer management practices