## Risk Value Map
ROUTES RISK VALUE MAP
Impact | 5 | Very High | 5 | 10 | 15 | 20 | 25
| 4 | High | 4 | 8 | 12 | 16 | 20
| 3 | Moderate | 3 | 6 | 9 | 12 | 15
| 2 | Minor | 2 | 4 | 6 | 8 | 10
| 1 | Insignificant | 1 | 2 | 3 | 4 | 5
Likelihood
|  |  | Remote < 3% | Minor >= 3% <10% | Moderate >= 10% <50% | High >= 50% <90% | Major >= 90%
|  |  | 1 | 2 | 3 | 4 | 5
Impact | Insignificant | No major impact on service delivery and reputation. Complaints and litigation are remote.
| Minor | Slight impact on service delivery and reputation. Complaints and litigation are possible.
| Moderate | Some service disruption and potential for adverse publicity. Avoidable with careful management. Complaints and litigation are probable.
| High | Service delivery is disrupted and adverse publicity is unavoidable. Complaints and litigation are probable.
| Very High | Service delivery is disrupted for significant time. Major adverse publicity is unavoidable. Major litigation is expected.
Resignation of senior management and/or Board exists. Widespread loss of benficiary confidence.
Likelihood | Remote | Theoretically possible, but not known to have occurred and is not expected to occur.
| Minor | Not expected to happen, but is possible.
| Moderate | Might happen or recur occassionally.
| High | Will probably happen/recur, but it is not a persisting issue/circumstances.
| Major | Will undoubtedly happen/recur, possibly frequently.
LEGEND:
RISK TYPE/CATEGORY:
| C | Compliance
| HR | Human Resources
| OP | Operational
| S | Strategic
| F | Financial
| MC | Marketing & Communications
| IT | Information Technology

## Risk Register & Plan Condensed
RISK REGISTER/RISK MANAGEMENT PLAN SAMPLE
Risk Identification |  |  | Risk Analysis | [12 empty] | Risk Management Plans
|  |  | Inherent Risk Assessment |  |  | Risk Mitigation - Controls/Actions Implemented |  |  | Risk Mitigation Reduction Score |  | Residual Risk Assessment |  |  | Risk Tolerance Assessment |  | Risk Management Change Initiatives - Controls/Actions to be Implemented where Risk Tolerance > Residual Risk
No. | Risk Description and Element(s) | Risk Type/Category | Impact (1-5) | Likelihood (1 - 5) | Risk Score (Impact X Likelihood) | Risk Response | Mitigating Factors: Controls/Actions in place to mitigate, reduce or eliminate risks | Reference Documents | Reduction to Impact (1-5) | Reduction to Likelihood (1 - 5) | Impact (1-5) | Likelihood (1 - 5) | Residual Risk (Impact X Likelihood) | Risk Tolerance (Impact X Likelihood) 1-25 | Residual Risk > Risk Tolerance | Change Initiatives - Controls/Actions to be implemented | Monitoring Oversight Responsibility | Last Review Date
C1 | Statutory and Regulatory Compliance | Compliance | 4 | 2 | 8 | Avoid | Annual review of current legs and regs; ongoing monitoring and assessment of proposed changes or new requirements; policies updated to be consistent with changes; legal advisors provide updates and insight; includes Ontario Human Rights Code. | Regular Handbook Review (Client, Employee and Volunteer) Accreditation compliance | 0 | 1 | 4 | 1 | 4 | 6 |  |  | Board, ED | May 28 2025
C2 | Non-Compliance with Policies and Procedures | Compliance | 4 | 2 | 8 | Mitigate | Performance reviews, policy training, manuals. | Employee Handbook; key policies signed at hire and annually; refreshers, performance management. | 0 | 1 | 4 | 1 | 4 | 12 |  | Electronic Signature and Attestation software to implement | Leadership Team | May 28 2025
C3 | Privacy Breach | Compliance | 4 | 1 | 4 | Avoid | Consent forms provided to clients. CHATS’ Privacy Officer audits client record sharing software monthly for privacy breaches. Training staff on protecting privacy. | Electronic records, Client consent forms, protection with Alayacare | 0 | 1 | 4 | 0 | 0 | 10 |  |  | Leadership Team | May 28 2025
C4 | Legal Claims | Compliance | 4 | 2 | 8 | Accept | Employment lawyer consulted for terminations and performance issues to minimize exposure. Work-related legal claims against CHATS are covered by CHATS Insurance. A thorough review of insurance coverage is conducted annually. Employment legislation followed. | Legal Action compliance policy | 1 | 1 | 3 | 1 | 3 | 6 |  |  | Board, ED, Management | May 28 2025
HR1 | Key Staff and Board Turnover | Human Resources | 4 | 2 | 8 | Mitigate | CHATS has clearly defined roles and responsibilities, terms of reference, and job descriptions. Succession plans in place for Board/committees, staff and CEO. Staff Satisfaction Surveys. Quarterly monitoring of turnover, annual review of job descriptions, succession plans etc. | Staff Performance Reviews tracked and trended. Review at leadership meetings and mitigation strategies developed | 1 | 0 | 3 | 2 | 6 | 4 |  |  | Board, ED, Management | May 28 2025
HR2 | Staff engagement | Human Resources | 3 | 2 | 6 | Mitigate | HR Plan, staff experience surveys every two years. Action plans created from survey results as appropriate. | Monthly team meetings Annual performance appraisals | 1 | 1 | 2 | 1 | 2 | 4 |  | Staff Experience Survey - bi-annual. | Leadership Team | May 28 2025
HR3 | Staff burnout | Human Resources | 4 | 3 | 12 | Mitigate | Employee & Family Assistance Program, resources sent in newsletter (e.g. mental health); additional supports (e.g. complementary meals for frontline workers/families); forums for employees to share thoughts/concerns (e.g. staff meetings); implemented frontline worker emergency fund Staff Experience Survey, Open Door Policy, RBC | Updated vacation allotment policy Promotion of flexible work chedules Staff recognition Regular Check-Ins and One-on-One Meetings | 2 | 1 | 2 | 3 | 6 | 6 |  | Staff Experience Survey - bi-annual. | ED | May 28 2025
HR4 | Volunteer Liability - client interaction, car accidents, adherence to policy | Operational | 3 | 2 | 6 | Mitigate |  | Volunteer handbook, volunteer training and onboarding requirements, vulnerable sector screening and driver abstracts | [7 empty] | Training refresh with volunteers on annual basis, overhauling the training and onboarding process. | Leadership Team
HR5 | Volunteer Recruitment Challenges | Operational | 2 | 5 | 10 | Mitigate |  | Volunteer handbook, strategic plan, monthly transportation reports | [7 empty] | Strategic outreach campaign to increase volunteer awareness and recruitment | Leadership Team
OP1 | Client Experience/Poor Coordination and Communication | Operational | 4 | 4 | 16 | Accept | Annual experience surveys with action plans. Quarterly quality indicator report. Target: >85% of clients describe overall experience as strongly agree | Annual experience surveys with action plans. Annual client feedback (compliment/complaint) reports. Reported annually to RCC board Ring Central reports | 0 | 0 | 1 | 3 | 3 | 3 |  |  | Leadership Team | May 28 2025
OP2 | Client and Caregiver Expectations | Operational | 2 | 3 | 6 | Mitigate | Supervisors conduct service assessments to mutually establish client/caregiver goals (reflective of their complexity with evidence based goals and interventions) and communicate the service plan and care plan interventions and outcome goals. Used also to prioritize waitlists if appropriate. InterRAI assessment tool for accurate assessment of client needs and risks. Monitor client's goals and needs over time. Monitor client feedback reports and maintain target levels. Open door policy and availability of staff to meet and discuss. Can suubmit complaint and compliment and feedback through Seniorshelp. Service Agreements and FACT sheets provide addiational information on eligibility and scope of program. | Assessments completed in Palamino. Processes for care planning outlined in Client Care & Services policies and procedures. | 0 | 0 | 2 | 3 | 6 | 6 |  | Assessments in Alayacare in the future | Leadership Team | May 28 2025
OP3 | Waitlists | Operational | 4 | 4 | 16 | Mitigate | Client Risk codes and prioritization ensure high risk clients are seen on a timely basis. New medication policy and protocols focused on risk mitigation and identification of high risk situations. Waitlists due staffing resources can result in clients not being served and service volumes not met. Waitlist times are monitored. Use of contracted out services minimize impact of staffing shortages, but may increase risk of quality because of lack of control: AL Shift Model roll out providing greater consistency in staffing. | Processes and policies for client care in Client Handbook Alignment with like-minded organizations policies | 0 | 0 | 4 | 4 | 16 | 12 |  | Recruit more volunteers | Leadership Team | May 28 2025
OP4 | Unmet Performance Requirements | Operational | 4 | 2 | 8 | Avoid | Inability to meet funder volume or unit cost requirements could result. To be compliant with MSAA volume targets (within corridor) and unit costs. Perform monthly variance analysis of indicators. If results are outside of the corridor, determine if substitutions are possible and/or develop strategies to meet corridor. Monthly reports of all costs and performance indicators are generated, reviewed by the management team and strategies are developed to ensure targets are met. | Leadership team reports/minutes. Reports of costs and performance indicators to funders | 1 | 1 | 3 | 4 | 12 | 15 |  | Goal setting across all programs and regular monitoring by supervisor. | Leadership Team | May 28 2025
OP5 | Incidents and Complaints | Operational | 3 | 4 | 12 | Mitigate | Reporting system for actual and potential adverse events, including appropriate follow-up in compliance with any applicable legislation; and within any protection afforded by legislation. Based on annual targets in QIP. | Incident and Feedback (compliments and complaints) review | 1 | 1 | 2 | 3 | 6 | 6 |  | Bi-annual Incident Reports Implement incident reporting system | Leadership Team | May 28 2025
OP6 | Disease Outbreak | Operational | 3 | 2 | 6 | Mitigate | Comprehensive infection prevention & control program to control and manage the spread of infection. Special emphasis on flu season concerns. Promotion of vaccination clinics for staff and clients. | Infection prevention and control measures | 1 | 1 | 2 | 2 | 4 | 6 |  |  | Leadership Team | May 28 2025
OP7 | Cash Handling | Operational | 3 | 3 | 9 | Avoid |  | Cash stored in secure location (locked safe) Count cash in secure non public area with multiple staff present Quarterly internal audits | 2 | 2 | 2 | 2 | 2 |  |  | Implmenet at least two new electronic or cash less projects | ED, Financial Administrator | May 28 2025
OP8 | Vehicle breakdown or accident (accessible van or bus) | Operational | 3 | 2 | 6 | Mitigate |  | Staff onboarding, training, bus and van schedules | [7 empty] | Recruiting experienced, safe, reliable staff to operate vehicles, ensuring adequate training, avoiding adverse driving conditions where possible, avoiding overscheduling or tight schedules where possible | Leadership Team
OP9 | Inadequate facilities / disordered staffing | Operational | 2 | 5 | 10 | Mitigate |  | Employee handbook, employee schedules, The Link lease | [7 empty] | Leverage hybrid schedules in a manner that minimizes disruption to service while maintaining a welcoming "no wrong door" approach. Office capacity dependent. | Leadership Team
S1 | Public Policy Changes/ Political Climate | Strategic | 4 | 4 | 16 | Accept | Monitor and assess changes to legislation (Bill 78). Strategically work with OCSA and other partners to address concerns, particularly as this relates to managing public policy issues related to pandemic, including changes in LTC (minimum hours for PSWs) and impact on home and community workforce. Build and maintain relationships with local and elected officials (all parties, all levels). Provide local leadership in the development and collation of feedback on relevant legislation and regulations. | Board and committee minutes, leadership team reports/minutes. Relationships with local MP and MPP's | 0 | 0 | 4 | 4 | 16 | 12 |  |  | Board, ED, Leadership Team | May 28 2025
F1 | Balanced Financial Results | Financial | 4 | 4 | 16 | Avoid | Monthly reviews of all costs, volumes and wait lists. Analysis of impact of unexpected threats/opportunities before decisions are made. | Monthly financial reports. Quarterly board reports Audited Financials Statements | 1 | 1 | 3 | 3 | 9 | 6 |  |  | Board, ED | May 28 2025
F2 | Cash Flow | Financial | 4 | 4 | 16 | Mitigate |  | Monthly Financial Reporting Grant Schedule A Matrix | 2 | 2 | 2 | 2 | 2 |  |  | Establish an AR strategy/schedule to rekindle money owed in a timely manner. | ED | May 28 2025
F3 | Funding Dependence - One Main Funder (ex York Region) | Financial | 5 | 4 | 20 | Accept | New funding model is unknown at this time - new model may cause significant change, but unkown. Membership with 3 OHTs, and involvement with others through their application process. Strategy includes plans to diversify revenue by increasing fund 3 activity (non-LHIN funding, e.g. planned giving), and to be in a position to respond to funding changes by Ontario Health. | Strategic Plan. Introduction to York Region Senior Services leadership Bi annual Strategic Plan updates. | 0 | 0 | 5 | 4 | 20 | 10 |  |  | Board, ED, Leadership Team | May 28 2025
IT1 | Cyber Security | Technology | 4 | 3 | 12 | Trasfer | Managed IT Service Provider in place to montior networks and systems and prevent cyber attackes. Training and reminders to staff to prevent phishing email incidents. Cyber security insurance in place. | Cyber security insurance policy. | 2 | 1 | 2 | 2 | 4 | 6 |  |  | Leadership Team | May 28 2025
Note on B1: Joanne Stolte:

## Risk Report Summary
Routes 2025- Q2
Risk Report Summary
4. Changes from prior Quarter:
| 5.a) Inherent Risk Changes: |  |  | Prior Quarter |  |  | Current Quarter
| Risk No. | Risk Category | Risk Element | Impact | Likelihood | Inherent Risk | Impact | Likelihood | Inherent Risk | Difference | Explanation
| S1 | Operational | Disease Outbreak-Non Pandemic | 2 | 2 | 4 | 3 | 3 | 9 | 5 | Increase opening of public spaces leading to spread of non COVID illnesses
| OP11 | Operational | Disease Outbreak-Pandemic | 5 | 3 | 15 | 5 | 5 | 25 | 10 | Increase opening of public spaces leading to spread of COVID
| 5. b) Residual Risk Changes: |  |  | Prior Quarter |  |  | Current Quarter
| Risk No. | Risk Category | Risk Element | Impact | Likelihood | Residual Risk | Impact | Likelihood | Residual Risk | Difference | Explanation
| OP10 | Operational | Disease Outbreak-Non Pandemic | 2 | 2 | 4 | 2 | 3 | 6 | 2 | Need for isolation due to exposure causing absences
| OP11 | Operational | Disease Outbreak-Pandemic | 4 | 3 | 12 | 4 | 5 | 20 | 8 | Need for isolation due to exposure causing absences and program closures
5. c) Risk Tolerance Changes:
NO CHANGES

## DO NOT PRINT (hidden)
Compliance
C1 | Statutory and Regulatory Compliance
C2 | Non-Compliance with Policies and Procedures
C3 | Privacy Breach
C4 | Legal Claims
C5 | Ethics
Human Resources
HR1 | Key Staff and Board Turnover
HR2 | Worker Shortage
HR3 | Staff engagement
HR4 | Credentials/Competence/Ongoing Learning
HR5 | Unionization
HR6 | Abuse – from workers and clients
HR7 | Occupational Health and Safety
HR8 | Staff Virtual Onboarding
HR9 | Staff Burnout
Operational
OP1 | Client Experience
OP2 | Client and Caregiver Expectations
OP3 | Client safety
OP4 | Waitlists
OP5 | Unmet Performance Requirements
OP6 | Reliance on Partner Infrastructure
OP7 | Professional Practice and Partnerships
OP8 | Incidents and Complaints
OP9 | Caseloads
OP10 | Disease Outbreak-Non Pandemic
OP11 | Disease Outbreak-Pandemic
OP12 | Facilities Sustainability
OP13 | Inclement Weather
Strategic
S1 | System Restructuring
S2 | Public Policy Changes/ Political Climate
S3 | Competition
S4 | Involuntary Integration
S5 | Health Equity
Financial
F1 | Balanced Financial Results (Fund 2)
F2 | Cost of service delivery
F3 | Misappropriation of Assets
Marketing and Communications
MC1 | Funding Dependence - One Main Funder
MC2 | Inconsistent Communications
Technology
IT1 | Cyber Security
IT2 | Critical System Outages
IT3 | System Transition
IT4 | Suboptimal Use of Technology Systems
IT5 | Operational Sustainability of Technology Systems
IT6 | Implementation of Incompatible/Low Value Adding Technology Systems

## Risk Index DONT PRINT (hidden)
Compliance
5 | C1 | Statutory and Regulatory Compliance
6 | C2 | Non-Compliance with Policies and Procedures
7 | C3 | Privacy Breach
8 | C4 | Legal Claims
9 | C5 | Ethics
Human Resources
10 | HR1 | Key Staff and Board Turnover
11 | HR2 | Worker Shortage
12 | HR3 | Staff engagement
13 | HR4 | Credentials/Competence/Ongoing Learning
14 | HR5 | Unionization
15 | HR6 | Abuse – from workers and clients
16 | HR7 | Occupational Health and Safety
Operational
17 | OP1 | Client Experience
18 | OP2 | Client and Caregiver Expectations
19 | OP3 | Client safety
20 | OP4 | Waitlists
21 | OP5 | Unmet Performance Requirements
22 | OP6 | Reliance on Partner Infrastructure
23 | OP7 | Professional Practice and Partnerships
24 | OP8 | Incidents and Complaints
25 | OP9 | Caseloads
26 | OP10 | Disease Outbreak-Non Pandemic
27 | OP11 | Disease Outbreak-Pandemic
Strategic
28 | S1 | System Restructuring
29 | S2 | Public Policy Changes/ Political Climate
30 | S3 | Competition
31 | S4 | Involuntary Integration
32 | S5 | Health Equity
Financial
33 | F1 | Balanced Financial Results
34 | F2 | Cost of service delivery
35 | F3 | Misappropriation of Assets
Marketing and Communications
36 | MC1 | Funding Dependence - One Main Funder
37 | MC2 | Inconsistent Communications
Technology
38 | IT1 | Cyber Security
39 | IT2 | Critical System Outages